## Sheet1
Risk ID | Risk Description | Cause | Impact | Likelihood (1–5) | Impact (1–5) | Risk Score | Control | Mitigation | Owner | Risk Level
R-01 | Excessive administrative access assigned to IAM user | Administrative access policy assigned | Unathorized system chnages or data breach | 4 | 5 | 20 | Least privilage access | Replace admin access with role based permissions | Cloud Admin | Critical
R-02 | IAM user does not have MFA enabled | MFA not configured | Account compromise | 4 | 5 | 20 | Multi-factor authentication | Enforce MFA for all users | Security Team | Critical
R-03 | S3 bucket allows public read access | Misconfigured bucket policy | Data exposure | 5 | 5 | 25 | Restrict public access | Block public access and tighten policies | Cloud Admin | Critical
R-04 | Insufficient cloud activity logging | CloudTrail not fully configured | Security incidents may not be detected or i nvestigated properly | 4 | 5 | 20 | Centralized logging and monitoring | Configure CloudTrail across all regions and monitor logs regularly | Secuirity Team | Critical